## Slide 1
MODERN SYSTEMS ANALYSIS & DESIGN
Managing the Information
Systems Project
CHAPTER 3
1

## Slide 2
OVERVIEW
Learning Objectives
1
Explain how information systems projects are managed from start to finish.
2
Describe the skills an effective project manager needs.
3
Identify the project manager's activities across initiation, planning, execution, and closedown.
4
Explain critical path scheduling, and how to build Gantt charts and network diagrams.
5
Explain how project management software supports scheduling and tracking.
2

## Slide 3
WHY IT MATTERS
Importance of Project Management
Project management, an important factor in whether a systems development effort succeeds.
Meets Customer Expectations
Effective PM keeps deliverables aligned with what the customer asked for.
Respects Budget & Time
It keeps the project inside the budget and schedule constraints set at the start.
PM skills are difficult to master — and important to keep sharpening.
3

## Slide 4
GETTING STARTED
Deciding on Systems Projects
System Service Request (SSR)
A standard form used to request or propose systems development work within an organization.
Feasibility Study
An assessment of whether a requested system makes economic and operational sense for the organization.
5

## Slide 5
EXAMPLE
A System Service Request in Practice
SYSTEM SERVICE REQUEST
REQUESTED BY
Leonard Jackson, Purchasing
DATE
October 1, 2026
DEPARTMENT
Manufacturing / Purchasing
TYPE OF REQUEST
New System
PROBLEM STATEMENT
Growing sales volume has outpaced what current systems can track.
LIAISON
Chris Martin, Purchasing
SPONSOR
V.P. of Manufacturing
What goes into an SSR
Who is requesting the system, and their contact information
A clear statement of the business problem
The liaison and sponsor who will support the project
FIGURE 3-2 — A Systems Priority Board reviews each SSR; limited time and resources mean not every request is approved.
6

## Slide 6
Managing the Information Systems Project
Project
A planned undertaking of related activities aimed at a single objective — with a defined beginning and end.
Project Management
The controlled process of initiating, planning, executing, and closing down a project.
Project Manager
A systems analyst with the management and leadership skills to lead initiation, planning, execution, and closedown.
Deliverable
The tangible end product produced at the close of an SDLC phase.

## Slide 7
Project Management Activities
A project manager juggles many concurrent activities — the role is a hub, not a single track.
Customer
Management
Team
Management
Risk &
Contingency
Change
Management
Methods &
Tools
Vendor
Coordination
Project
Manager
9

## Slide 8
ROADMAP
Phases of the Project Management Process
PHASE 1
Initiation
PHASE 2
Planning
PHASE 3
Execution
PHASE 4
Closedown
10

## Slide 9
PHASE 1
Project Initiation
Assess the project's size, scope, and complexity, and put initial procedures in place.
Initiation team
Customer relationship
Project initiation plan
Management procedures
Project management environment
Project workbook
11

## Slide 10
FIGURE 3-6 (RECREATED)
The Project Workbook
PROJECT
WORKBOOK
Project overview
Original SSR & feasibility study
Scope statement & staffing plan
Data & process descriptions
Team correspondence
Project schedule & charter
Standards & procedures
Status reports
Change requests
Nine key documents, kept in both hard-copy and electronic form throughout the project.
12

## Slide 11
PHASE 2
Project Planning
Define clear, discrete activities and the work needed to complete each one.
1
Define scope, alternatives & feasibility
2
Divide the project into tasks
3
Estimate resource requirements
4
Draft a preliminary schedule
5
Develop a communication plan
6
Set standards & procedures
7
Identify and assess risk
8
Create a preliminary budget
9
Write a statement of work
10
Set the baseline project plan
13

## Slide 12
Planning Detail Over Time
High
Medium
Low
Level of Planning Detail
1 Week Out
1 Month Out
6 Months Out
Planning Horizon
Planning detail should be high for the near term, with less detail the further out the plan reaches.
14

## Slide 13
PLANNING DELIVERABLES
Components of Project Planning
Statement of Work (SOW)
A “contract” between IS staff and the customer covering deliverables and time estimates.
Baseline Project Plan (BPP)
Estimates of scope, benefits, schedules, costs, risks, and resource needs.
Preliminary Budget
A cost-benefit analysis outlining planned expenses and revenues.
15
Work Breakdown Structure
Dividing the project into manageable, logically ordered tasks and subtasks.
Gantt Chart
Horizontal bars represent task durations, laid out on a timeline.
Network Diagram
Boxes and links represent dependencies between tasks.

## Slide 14
Scheduling Diagrams: Gantt Chart
0d
2d
4d
6d
8d
10d
12d
14d
Define Requirements
Design Interview Form
Schedule Appointments
Conduct Interviews
Review Current Reports
Collect Reports
Summarize Results
Gantt chart showing project tasks, their durations, and how they overlap on a shared timeline (in days).
Special-purpose project management software is available for this.
17

## Slide 15
Scheduling Diagrams: Network Diagram
Define
Requirements
Design
Interview Form
Review
Reports
Schedule
Appointments
Collect
Reports
Conduct
Interviews
Summarize
Results
Deliver
Findings
Rectangles represent tasks; arrows show the sequence and dependencies between them.
Special-purpose project management software is available for this.
18
Ch. 3 — Managing the Information Systems Project

## Slide 16
FIGURE 3-15 (RECREATED)
Preliminary Budget
Chart: Cost – Benefit Analysis
| Year 1 | Year 2 | Year 3
Planned Expenses | 42000 | 28000 | 22000
Planned Benefits | 10000 | 46000 | 61000
A financial cost-and-benefit analysis for a systems development project. Spreadsheet software is well suited to this.
19
Ch. 3 — Managing the Information Systems Project

## Slide 17
PHASE 3
Project Execution
Plans created in the prior phases are put into action.
Execute the baseline project plan
Monitor progress against the baseline
Manage changes to the baseline plan
Maintain the project workbook
Communicate project status
20
Ch. 3 — Managing the Information Systems Project

## Slide 18
FIGURE 3-17 (RECREATED)
Monitoring Progress with a Gantt Chart
0d
2d
4d
6d
8d
10d
12d
14d
Define Requirements
Design Interview Form
Schedule Appointments
Conduct Interviews
Review Current Reports
Collect Reports
Summarize Results
Critical path
Percent complete
21
Ch. 3 — Managing the Information Systems Project

## Slide 19
STAYING ALIGNED
Communication Methods
High Formality
Project workbook · Status reports · Specification documents · Meeting minutes
Medium Formality
Meetings · Seminars & workshops · Memos
Low Formality
Bulletin boards · Brown-bag lunches · Hallway discussions
22
Ch. 3 — Managing the Information Systems Project

## Slide 20
PHASE 4
Project Closedown
Bring the project to a formal end.
Close down the project
Conduct post-project reviews
Close the customer contract
23
Ch. 3 — Managing the Information Systems Project

## Slide 21
COMING UP
Representing and Scheduling Project Plans
Gantt Charts
Network Diagrams
PERT Calculations
Critical Path Scheduling
Project Management Software
24
Ch. 3 — Managing the Information Systems Project

## Slide 22
COMPARISON
Gantt Charts vs. Network Diagrams
Gantt Charts
Show task durations
Show time overlap
Show slack time within a bar's duration
Network Diagrams
Show task dependencies
Show parallelism, not time overlap
Show slack time inside the boxes
25
Ch. 3 — Managing the Information Systems Project

## Slide 23
SCHEDULING MATH
Estimating Task Duration with PERT
PERT — Program Evaluation Review Technique
Combines an optimistic (o), pessimistic (p), and realistic (r) time estimate to produce one expected task duration.
ET = ( o + 4r + p ) / 6
o
Optimistic time
r
Realistic (most likely) time
p
Pessimistic time
ET
Expected task duration
26
Ch. 3 — Managing the Information Systems Project

## Slide 24
Example PERT Analysis
Activity | o | r | p | Expected Time (ET)
1. Requirements Collection | 1 | 5 | 9 | 5.0
2. Screen Design | 5 | 6 | 7 | 6.0
3. Report Design | 3 | 6 | 9 | 6.0
4. Database Design | 1 | 2 | 3 | 2.0
5. User Documentation | 2 | 6 | 7 | 5.5
6. Programming | 4 | 5 | 6 | 5.0
7. Testing | 1 | 3 | 5 | 3.0
8. Installation | 1 | 1 | 1 | 1.0
Estimated time calculations for the project, using ET = (o + 4r + p) / 6.
27
Ch. 3 — Managing the Information Systems Project

## Slide 25
SCHEDULING MATH
Critical Path Scheduling
A scheduling technique in which the order and duration of a sequence of activities directly determines the project's completion date.
Critical Path
The shortest time in which the entire project can be completed — its longest chain of dependent tasks.
Slack Time
The amount an activity can be delayed without pushing back the overall project.
28
Ch. 3 — Managing the Information Systems Project

## Slide 26
Critical Path Example: Dependencies
Activity | Preceding Activity
1. Requirements Collection | —
2. Screen Design | 1
3. Report Design | 1
4. Database Design | 2, 3
5. User Documentation | 4
6. Programming | 4
7. Testing | 6
8. Installation | 5, 7
A preceding activity must finish before the specified activity can begin.
This dependency table is the direct input to the network diagram on the next slide.
29
Ch. 3 — Managing the Information Systems Project

## Slide 27
Critical Path Example: Network Diagram
1
2
3
4
5
6
7
8
Circles represent activities; arrows show the sequence between them.
Network diagram showing dependencies for the same eight activities.
30
Ch. 3 — Managing the Information Systems Project

## Slide 28
METHOD
Determining the Critical Path
1
Forward Pass
Calculate each activity's earliest possible completion time by summing activity times along the longest path leading to it. This gives the total expected project time.
2
Backward Pass
Calculate each activity's latest possible completion time by subtracting the activity times on the path that follows it from the total expected time. This gives each activity's slack.
3
Identify the Path
The critical path is the chain of activities with zero slack — any delay there delays the whole project.
31
Ch. 3 — Managing the Information Systems Project

## Slide 29
Critical Path Calculation
1
ES 0 | LS 0
2
ES 5 | LS 5
3
ES 5 | LS 5
4
ES 13 | LS 13
5
ES 18.5 | LS 21
6
ES 18 | LS 18
7
ES 21 | LS 21
8
ES 22 | LS 22
Early and late times are calculated for each activity; Activity 5 can begin late without affecting the finish date.
32
Ch. 3 — Managing the Information Systems Project

## Slide 30
Critical Path Calculation (cont.)
Activity | TE | TL | Slack (TL − TE) | On Critical Path
1 | 5 | 5 | 0 | ✓
2 | 11 | 11 | 0 | ✓
3 | 11 | 11 | 0 | ✓
4 | 13 | 13 | 0 | ✓
5 | 18.5 | 21 | 2.5 | —
6 | 18 | 18 | 0 | ✓
7 | 21 | 21 | 0 | ✓
8 | 22 | 22 | 0 | ✓
Every activity except Activity 5 sits on the critical path — note its 2.5-day slack.
33
Ch. 3 — Managing the Information Systems Project

## Slide 31
TOOLS
Using Project Management Software
Many powerful software tools exist to assist with project management — Microsoft Project is a common example.
Enter the project start date
Establish tasks and task dependencies
View project information as Gantt or network diagrams
34
Ch. 3 — Managing the Information Systems Project

## Slide 32
Setting the Project Start Date
PROJECT INFORMATION
Project Start Date
March 3, 2027
Scheduling mode: Auto · Calendar: Standard (5-day week)
Save
Every schedule anchors to a starting date; the software calculates every other date from there.
35
Ch. 3 — Managing the Information Systems Project

## Slide 33
Entering Tasks and Dependencies
Task Name | Duration | Predecessors
1. Define Requirements | 6 days | —
2. Design Interview Form | 1 day | 1
3. Schedule Appointments | 1 day | 2
4. Conduct Interviews | 4 days | 3
5. Review Current Reports | 2.5 days | 1
6. Collect Reports | 0.5 days | 1
7. Summarize Results | 2 days | 4, 6
Once tasks, durations, and predecessors are entered, the software builds the Gantt and network views automatically.
36
Ch. 3 — Managing the Information Systems Project

## Slide 34
Viewing a Network Diagram in Software
Define
Requirements
Design
Interview Form
Review
Reports
Schedule
Appointments
Collect
Reports
Conduct
Interviews
Summarize
Results
Milestone:
Complete
Milestone
Critical path (no slack)
37
Ch. 3 — Managing the Information Systems Project

## Slide 35
Viewing a Gantt Chart in Software
0d
2d
4d
6d
8d
10d
12d
14d
Purchasing Overview
Define Requirements
Design Interview Form
Conduct Interviews
Review Current Reports
Project Kickoff
Summary activity
Critical path
Percent complete
Milestone
38
Ch. 3 — Managing the Information Systems Project

## Slide 36
CHAPTER RECAP
Summary
How information systems projects are managed from initiation through closedown.
The skills an effective project manager needs.
The project manager's activities across each of the four PM phases.
Critical path scheduling, and how to build Gantt charts and network diagrams.
How project management software supports scheduling and tracking.
Thank you.
39
Ch. 3 — Managing the Information Systems Project