## Slide 1
University Event Management System (UEMS)
Project Management Plan
IT 612 – Project Management in IT
Prepared by: Md. Shakil Hossain | Supervised by: Dr. Shabana Habib
QASSIM UNIVERSITY | College of Computer | Department of Information Technology | 2026

## Slide 2
Presentation Agenda
01
Introduction
Background, Problem Statement & Objectives
02
Project Charter
SMART Goals, Stakeholders & Constraints
03
Scope & Schedule
WBS, Gantt Chart & Critical Path
04
Cost & Quality
Budget SAR 285K, Standards & Acceptance
05
Risk & HR
12-Risk Register, RACI Matrix & Team
06
Communication & Procurement
Matrix, Tools, Strategy & Vendors

## Slide 3
Introduction & Problem Statement
Organizational Background
• Qassim University – established 2004, Buraidah, KSA
• 60,000+ students; under Ministry of Education
• College of Computer, Dept. of Information Technology
• Programs aligned with Vision 2030 digital economy
• Manages 100s of academic & non-academic events/year
Current Problems
• Scheduling conflicts – no central venue booking
• Communication gaps between organizers & participants
• Budget mismanagement – informal financial tracking
• Inefficient registration – paper-based, time-consuming
• No event history or analytics for decision-making
• Estimated cost: SAR 120,000+/year in lost productivity

## Slide 4
Project Charter & SMART Objectives
Sponsor
Qassim University Rector's Office
Duration
10 Weeks Feb – Apr 2026
Budget
SAR 285,000
Priority
HIGH – Strategic Digital Transform.
SMART Objectives
S – Specific
Develop centralized web-based UEMS for Qassim University
M – Measurable
Reduce scheduling conflicts 90% & manual time 75% within 6 months
A – Achievable
Complete planning in 10 weeks using QU IT expertise & infrastructure
R – Relevant
Aligned with QU digital transformation & Saudi Vision 2030 e-governance
T – Time-bound
Full Project Management Plan delivered by April 30, 2026

## Slide 5
Scope Management & Work Breakdown Structure
✓ In Scope
• Event creation & management module
• Participant registration (email/SMS notifications)
• Venue/resource booking with conflict detection
• Budget management with approval workflow
• Attendance tracking (QR-code check-in)
• Post-event feedback & survey module
• Role-based access (Admin/Coordinator/Faculty/Student)
• MyQU portal SSO integration
• Bilingual interface (Arabic & English)
• System testing plan (unit, integration, UAT)
✗ Out of Scope
• Actual software coding
• Hardware infrastructure setup
• Post-deployment training
• 3rd-party platform integration
• Mobile app (iOS/Android)
WBS Top-Level Components
• 1.0 Project Management
• 2.0 Requirements
• 3.0 System Design
• 4.0 Development (6 modules)
• 5.0 Integration & Testing
• 6.0 Documentation
• 7.0 Deployment

## Slide 6
Schedule Management – Gantt & Critical Path
Activity
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
Project Charter
Requirements
Scope & WBS
Cost & Budget
Risk Analysis
Architecture Design
Wireframes
Plan Review
Final Report
Submission
Critical Path: A1→A3→A4→A6→A10→A13→A14→A15→A16 | Total Float: 0 | Duration: 37 days | Schedule tracked via EVM (SPI metric)

## Slide 7
Cost Management – Budget SAR 285,000
Cost Item
SAR Amount
% of Total
Project Manager (400 hrs × SAR 200)
80,000
28.1%
Senior Developers ×2 (480 hrs × SAR 175)
84,000
29.5%
Business Analyst (160 hrs × SAR 150)
24,000
8.5%
UI/UX Designer (120 hrs × SAR 140)
16,800
5.9%
QA/Test Engineer (120 hrs × SAR 130)
15,600
5.5%
SMS Gateway API (12 months)
18,000
6.3%
Email Service – SendGrid (12 months)
9,000
3.2%
Cloud Hosting VPS (2 years)
15,000
5.3%
QR Scanner Hardware (×5 units)
4,000
1.4%
UAT Coordination
5,000
1.8%
TOTAL DIRECT COSTS
271,400
+10% contingency → SAR 298,540 total

## Slide 8
Risk Management – 12-Risk Register
ID
Risk
Rating
Score
Strategy
R01
Scope change after baseline
High
4×4=16
Enforce change control; freeze scope Wk 3
R02
Key team member unavailable
High
3×4=12
Cross-train team; maintain skills matrix
R03
MyQU portal integration failure
Critical
4×5=20
Early API testing; involve QU IT from Wk 2
R04
Budget overrun – licensing costs
Medium
2×4=8
Prefer open-source; 10% contingency reserved
R05
Late requirements sign-off
High
4×4=16
Hard approval deadlines; early escalation
R06
Data privacy breach in test env.
High
2×5=10
Anonymized test data; NCA ECC controls
R07
Poor user adoption
Medium
3×3=9
Involve users in UAT; conduct training
R08
Vendor delay for QR hardware
Low
2×3=6
Order early Wk 3; identify backup vendor
R09
Technical debt from rushed dev
High
3×4=12
Enforce code review; no-shortcuts policy
R10
Arabic/English miscommunication
Medium
3×3=9
Bilingual minutes & documentation
R11
Scope creep – informal requests
High
4×3=12
Formal change control; stakeholder education
R12
Insufficient testing time
High
3×4=12
Parallel dev/testing; buffer in Wks 8–9

## Slide 9
Human Resource & Communication Management
Project Team (Matrix Structure)
Project Manager
100%
Overall planning, reporting, stakeholder comm.
Business Analyst
75%
Requirements gathering, WBS, scope docs
Lead Architect
60%
System architecture, tech selection, design
Senior Developer A
100%
Event, Registration & Database modules
Senior Developer B
100%
Budget, Attendance, Feedback & API modules
UI/UX Designer
80%
Wireframes, prototypes, bilingual design
QA/Test Engineer
100%
Test planning, execution, UAT coordination
IT Infrastructure
25%
Server setup, network, deployment env.
Communication Matrix
Weekly Status Report
Sponsor, IT Head
Sunday Email + SharePoint
Team Stand-up Meeting
Project Team
Monday 9AM – MS Teams
Phase Gate Review
All Stakeholders
End of phase – In-person
Risk Log Update
PM + Leads
Bi-weekly SharePoint
Change Request Notif.
Relevant Parties
As needed – Email/CRF
Student/Faculty Bulletin
All QU Users
Monthly – MyQU Portal
Final Presentation
All Stakeholders
Week 10 – In-person

## Slide 10
Stakeholder Management – Power/Interest Grid
HIGH POWER
LOW POWER
LOW INTEREST
HIGH INTEREST
KEEP SATISFIED
QU Finance Dept. NCA (Regulator)
MANAGE CLOSELY
Rector's Office IT Dept. Head QU IT Infrastructure
MONITOR
External Vendors
KEEP INFORMED
Students Faculty Members Event Coordinators
Engagement Strategies
Manage Closely
Weekly status meetings, direct involvement in phase gates, proactive issue escalation, dedicated relationship log
Keep Satisfied
Monthly summary reports, formal compliance docs, engagement at milestones and financial/regulatory approvals
Keep Informed
Monthly MyQU bulletins, UAT participation, feedback surveys, active input in requirements & testing
Monitor
Procurement processes and contract performance management; updates only as relevant to deliverables

## Slide 11
Conclusion
Comprehensive Plan
Covers all 13 PMBOK knowledge areas. Includes Charter, WBS, Gantt chart, cost baseline, quality standards, RACI matrix, 12-risk register, procurement plan & stakeholder engagement strategy.
Strategic Alignment
UEMS directly supports Qassim University's digital transformation & Saudi Vision 2030 e-governance goals. Replaces fragmented manual processes with a centralized, bilingual, role-based digital platform.
Measurable Outcomes
90% reduction in scheduling conflicts. 75% reduction in manual processing time. SAR 120K+ annual savings expected. ROI within 18 months of deployment. System uptime ≥ 99.5%.
Budget: SAR 285,000 | Duration: 10 Weeks (Feb–Apr 2026) | Prepared by: Md. Shakil Hossain | Supervised by: Dr. Shabana Habib